## Visit Plan
Visit ID | Fictional Site ID | Supervisor ID | Priority | Due Date | Planned Start Date | Planned Start Time | Planned Duration (hours) | Status | Actual Completion Date | Planning Notes | Planned Start | Planned End | Due Indicator | Record Check | Counted Planned Hours
VIS-01 | SITE-A | SUP-A | High | 2026-09-27 | 2026-09-28 | 8:00 | 2 | Planned |  | Fictional example: priority review; planned after due date.
VIS-02 | SITE-B | SUP-A | Medium | 2026-09-28 | 2026-09-28 | 10:30 | 2 | Planned |  | Fictional example: scheduled site visit.
VIS-03 | SITE-C | SUP-A | Routine | 2026-09-29 | 2026-09-28 | 13:00 | 3 | Planned |  | Fictional example: combined day-zero load exceeds capacity.
VIS-04 | SITE-D | SUP-B | Medium | 2026-09-29 | 2026-09-29 | 9:00 | 1.5 | Planned |  | Fictional example: first day-one visit.
VIS-05 | SITE-E | SUP-B | Routine | 2026-09-30 | 2026-09-29 | 13:00 | 1.5 | Planned |  | Fictional example: second day-one visit.
VIS-06 | SITE-F |  | High | 2026-09-26 |  |  |  | Unscheduled |  | Fictional example: overdue; supervisor and schedule not assigned.
VIS-07 | SITE-G | SUP-A | Routine | 2026-09-28 | 2026-09-28 | 17:00 | 2 | Canceled |  | Fictional example: canceled visit contributes no planned hours.
VIS-08 | SITE-H | SUP-C | Medium | 2026-09-28 | 2026-09-28 | 9:00 | 1 | Completed | 2026-09-28 | Fictional example: manually recorded completion, not attendance evidence.
VIS-09 | SITE-I | SUP-C | High | 2026-09-30 | 2026-09-30 | 23:00 | 2 | Planned |  | Fictional example: overnight visit ends on day three at 01:00.
VIS-10 | SITE-J | SUP-B | Medium | 2026-09-29 | 2026-09-29 | 15:00 |  | Planned |  | Fictional example: duration missing; excluded from planned hours.
Formulas:
Due Indicator = IF([Visit ID]="","",IF([Status]="Canceled","Canceled",IF([Status]="Completed","Completed",IF([Due Date]="","Missing due date",IF(NOT(ISNUMBER([Due Date])),"Invalid due date",IF([Due Date]<TODAY(),"Overdue",IF([Due Date]=TODAY(),"Due today","Upcoming")))))))

## Daily Workload
Date | Supervisor ID | Planned Visits | Planned Hours | Capacity (hours) | Remaining Capacity (hours) | Alert | Records needing review; incomplete plans may be excluded
Planning workload only; not actual attendance or worked hours.
Completed visits retain planned hours. Canceled and unscheduled visits do not count.
Overnight hours stay on the start date. Travel, breaks, and overlaps are not calculated.
Initial fictional example: SUP-A day zero has 3 visits, 7.00 hours, and -1.00 hour remaining.

## Settings
Planning Control | Editable Value | Fictional Supervisor ID | Daily Visit Capacity (hours) | Priorities | Statuses | Use, Assumptions, and Calculation Notes
Week Start Date | 2026-09-28 | SUP-A | 6 | High | Unscheduled | All ten seeded visits, sites, and supervisor IDs are fictional examples. Replace or clear examples before operational use.
|  | SUP-B | 5 | Medium | Planned | Filter Visit Plan by due indicator, priority, supervisor, or record check. Assign supervisors and move planned dates manually.
Earliest Allowed Date | 2021-01-01 | SUP-C | 4 | Routine | Completed | Daily Workload has exactly seven days and three supervisor slots per day. Changing Week Start Date changes the view without deleting visits.
Latest Allowed Date | 2031-12-31 |  |  |  | Canceled | Capacities are editable planning assumptions, not staffing requirements, legal limits, or guarantees. Zero capacity is permitted.
Maximum Visit Duration (hours) | 24 |  |  |  |  | Duration excludes travel and breaks. Allow for both when setting daily visit-hour capacity. No paid or billable hours, rates, or payments are calculated.
Maximum Daily Capacity (hours) | 24 |  |  |  |  | Use one site-local time zone per workbook. Overnight visits count entirely on their start date; their end timestamp shows the next date. Overlaps are not detected.
Completion dates are manually recorded visit outcomes, not proof of guard attendance. Completed visits retain their planned workload; actual worked hours are not calculated.
Cream cells are editable. White and sage cells are calculated. Warnings also have text labels; highlighted IDs identify duplicates.
Use unique, nonblank supervisor IDs and numeric capacities. Keep the four status labels unchanged because formulas use those meanings. High is the highlighted priority.
Date bounds and maximum duration/capacity controls are editable here. Times run from 00:00 through 23:59. Durations must be positive and no greater than the maximum.
The review count is beside the Daily Workload header so the calendar retains records in rows 2–22. Incomplete plans may be excluded; review Visit Plan before relying on totals.
Dropdowns reference Settings cells without named ranges. Unknown IDs and invalid or incomplete inputs remain visible in Record Check.
Python checks formula coverage, input boundaries, and an independent workload model. Excel or LibreOffice must recalculate formulas; openpyxl does not calculate or cache results.